Yemen National Midwives Association - (NYMA)

Monitoring, Evaluation, learning and Accountability Manual

Introduction

Project management has the task of establishing sufficient controls over a project to ensure that it stays on track towards the achievement of its objectives. This is done by monitoring (internal), which is the systematic and continuous collection, analysis and use of information for management control and decision-making.

In this instance implementation is seen as a continuous learning process where experience gathered is analysed and fed back into planning and updated implementation approaches.

Monitoring is a continuous assessment of project implementation in relation to agreed schedules, use of inputs, infrastructure and services provided by project beneficiaries.

Evaluation on the other hand, is a periodic assessment of the relevance, performance efficiency and impact (both expected and unexpected) of the project in relation to stated objectives. Depending on its specific purpose, a high-quality evaluation provides information that enables the improvement of an on-going project, judgment on the overall merits of a project, or generation of knowledge about what works and what doesn’t to influence  NYMA’s strategy and policy.

Hence, the monitoring and evaluation play a complementary role.

In carrying out the monitoring or evaluation process, one or more of the following criteria shall be considered:

1. Relevance – The extent to which the objectives of a development intervention are consistent with beneficiaries’ requirements, country needs, institutional priorities and partner and Donor policies. It also entails an assessment of project coherence in achieving its objectives.

2. Efficiency – A measure of how economically resources/ inputs (funds, expertise, time, etc.) are converted into results.

3. Effectiveness – The extent to which the development intervention’s objectives were achieved, or are expected to be achieved, taking into account their relative importance.

4. Impact – Impact is defined as the changes that have occurred or are expected to occur in the lives of the rural poor, farmers, and the agriculture (whether positive or negative, direct or indirect, intended or unintended) as a result of development interventions.

5. Sustainability – The likely continuation of net benefits from a development intervention beyond the phase of external funding support. It also includes an assessment of the likelihood that actual and anticipated results will be resilient to risks beyond the project’s life.

While monitoring naturally includes elements of evaluation, there are clear differences between the two processes. The table below outlines those differences.

Differences between Monitoring and Evaluation

| Monitoring | Evaluation |
| --- | --- |
| Provides information enabling management personnel to assess implementation progress and make timely decisions | Relies on more detailed data (e.g., from surveys , studies, records, and reports) in addition to that collected through the monitoring system to understand the project in greater depth |
| Is concerned with verifying that project activities are being undertaken, services are being delivered, and the project is leading to the desired behaviour changes described in the project proposal | Assesses higher level outcomes and impact and may verify some of the findings from the monitoring process |
| Assessments should explore both anticipated and unanticipated results | Is an internal project activity. Can be externally led (particularly end of- project evaluations), though should involve the project staff for active participation |
| Is an essential part of good day-to-day management practice | Is an essential activity in a longer-term dynamic learning process |
| Is an essential part of management and must be integrated within the project management structure | Is important for making decisions on overall project direction |

| Takes place during the implementation phase | Occurs at pre-determined points during implementation. Other smaller evaluations may be undertaken to meet specific information needs throughout the process |
| --- | --- |
| Generally focuses on the question “Are we doing things right?” | Generally focuses on the question “Are we doing the right thing?” |

Monitoring and Evaluation (M&E) is a support activity intended to enhance the work of those involved in project management and implementation. M&E must never become so burdensome that it slows down implementation. If this is the case, the M&E system set up should be revisited during detailed implementation planning, and always question whether too much information is being collected or if enough time, staff, and financial resources have been allocated to collect the important data.

For M&E to work as a tool for managing impact,  NYMA project management and the M&E staff need to be clear on how to identify, agree upon and follow up on project improvements. If this process for guiding changes is not in place, even a very good M&E system will not have much value for the project.

Purpose of M&E

M&E is an important management function to track progress and support the decision-making process. It aims to meet the requirements of a number of financiers, but also of partners and targeted communities that work directly with  NYMA, who benefit most from the communicating progress through the M&E system. Through a thorough review of work progress,  NYMA can design programs and activities more effectively and ensure greater benefits to the project target group.

All projects gather information to assess progress against implementation plans (monitoring), and all projects gather information to assess the outcomes and impact it has achieved (evaluation). Good projects collect accurate information and produce timely reports. Great projects collect accurate information, and not only produce good reports, but take a step further and use the information to make decisions that improve efficiencies and enhance impact. The purpose of monitoring and evaluation is

to obtain accurate information that will be used by decision-makers in the project to improve and ensure proper use of resources as well as to maximize the results and benefits achieved from these resources.

Objectives of M&E

The project’s M&E system is built on the work undertaken during project design. A key feature of this work is the identification of a set of objectives, structured in a manner that provides a firm foundation for the design, establishment, and operation of the M&E system.

The M&E system in  NYMA is expected to achieve the following four objectives:

1 - Monitor and Manage Project Progress. Information will be obtained to measure the progress of the project against planned activities and production of outputs. This will also include assessing the quality of the activities and outputs toward achieving the desired outcomes. The information will be used by decision-makers to adjust plans by expanding activities that produce results at a reasonable cost, modifying activities that need to produce greater results or be implemented efficiently and discontinuing activities that are producing unsatisfactory results.

2 - Assess Project Outcomes and Impact.  NYMA M&E system will obtain information to enable decision-makers to assess the short- and medium-term effects of project interventions (outcomes), towards achieving impact on targeted impact groups  and in making contributions toward higher level impact. Outcome-level results assessment will focus on changes in behavior or systems as a result of project outputs. At the objective-level, the M&E system will obtain information to assess the likely long-term impact of the project on the lives of targeted impact groups. At the goal-level, the project M&E systems will provide information to assess the overall change, from all combined factors, toward meeting the goals of the program. The information obtained will be used by decision-makers to make modifications to the project strategy, reallocating resources, as required.

3 - Capture and Disseminate Lessons Learned and Good Practices. The project will generate useful lessons learned, both positive and negative, on implementation and impact as well develop good practices for achieving impact. The  NYMA M&E system will systematically capture these and ensure that they are not only well documented, but widely disseminated within the project as well as outside of the project. In addition, good practices and lessons learned from outside the project will be channeled into the project to be adapted and tested.

4 - Build Local Capacities for M&E. Finally, the M&E system has a specific objective to build capacities among beneficiaries to be able to undertake effective monitoring and evaluation using cutting edge ideas and technologies. The project management shall produce clear plans for gathering, recording, analysing and presenting information tailored to stakeholder needs, and for sharing such information across departments at different levels and with community and other beneficiaries.

Key Principles of the M&E Function

As an agent of development,  NYMA stands in service to the poor, marginalized and affected people , being responsible to engage and empower communities in programs that improve and enrich their lives.  NYMA is entrusted with significant resources to support humanitarian and development efforts for which it is held accountable. Thus, undertaking good quality M&E will promote better learning and strengthen accountability to stakeholders (beneficiaries).

M&E is guided by the following key principles:

1. Systematic Inquiry – Staff conduct site-based inquiries that gather both quantitative and qualitative data in a systematic and high-quality manner.

2. Honesty/Integrity – Staff display honesty and integrity in their own behavior and contribute to the honesty and integrity of the entire M&E business process.

3. Respect for People – Staff respects the security, dignity, and self-worth of respondents, program participants, clients, and other M&E stakeholders.

4. Responsibilities to beneficiaries – Staff members articulate and take into account the diversity of different beneficiaries’ interests and values that are relevant to project M&E activities.

Basic concepts of Monitoring and Evaluation

Results-based management (RBM)

RBM is an approach to  NYMA’s project management based on clearly defined results, including the methodologies and tools to measure and achieve them.

RBM supports better performance and greater accountability by applying a clear, logical framework to plan, manage and measure an intervention with a focus on the results needed to be achieved. By identifying in advance the intended results of a project and how progress can be measured, the project can be better managed.

As the M&E system of  NYMA is a results-based system which will focus not just on how well the activities of the project are being executed, but also on answering the question “have the goals and objectives of the project been achieved; and how is this supported by evidence?” Rather than focusing on how much output is being generated by the project, the monitoring and evaluation system will use survey data, qualitative information and self-assessments by participants to measure behavioural and systematic changes, as well as how these changes are affecting the lives of targeted beneficiaries.

-	M&E is a critical part of RBM.

M&E forms the basis for clear and accurate reporting on the results achieved by an intervention (project). In this way, information reporting becomes an opportunity for critical analysis and organizational learning, informing decision-making and impact assessment.

| Objective Hierarchy Links to Monitoring & Evaluation |  |
| --- | --- |
| Level in project hierarchy | What to monitor and evaluate |
| Goal (Impact) | To what extent has the project contributed towards its longer term goals? Why or why not? What unanticipated positive or negative consequences did the project have? Why did they arise? |
| Purpose/objectives (Outcome) | What changes have occurred as a result of the outputs and to what extent are these likely to contribute towards the project purpose and desired impact? Has the project achieved the changes for which it can realistically be held accountable? |
| Outputs | What direct tangible products or services has the project delivered as a result of activities? |
| Activities | Have planned activities been completed on time and within the budget? What unplanned activities have been completed? |
| Inputs | Are the resources being used efficiently? |

Baseline and endline studies

A baseline study is an analysis describing the initial conditions (appropriate indicators) before the start of a project/program, against which progress can be assessed or comparisons made. An endline study is a measure made at the completion of a project/program (usually as part of its final evaluation), to compare with baseline conditions and assess change. Baseline and endline studies are discussed together because if a baseline study is conducted, it is usually followed by another similar study later in the project/program (e.g. an end line study) for comparison of data to determine impact.

Baseline and end line studies are not evaluations themselves, but an important part of assessing change. They usually contribute to project evaluation (e.g. a final or impact evaluation), but can also contribute to monitoring changes on longer-term projects. The benchmark data from a baseline is used for comparison later in the project and/or at its end (end line study) to help determine what difference the project has made towards its objectives.

Minimize bias and error

M&E helps uphold accountability, and should therefore be accountable by itself. This means that the M&E process should be accurate, reliable and credible with beneficiaries. Consequently, an important consideration when doing M&E is that of bias. Bias occurs when the accuracy and precision of a measurement is threatened by the experience, perceptions and assumptions of the researcher, or by the tools and approaches used for measurement and analysis. Minimizing bias helps to increase accuracy and precision.

Accuracy means that the data measures what it is intended to measure. For example, if you are trying to measure knowledge change following a training session, you would not just measure how many people were trained but also include some type of test of any knowledge change.

Similarly, precision means that data measurement can be repeated accurately and consistently over time and by different people.

As much as we would like to eliminate bias and error in our measurements and information reporting, no research is completely without bias. Nevertheless, there are precautions that can be taken, and the first is to be familiar with the major types of bias personnel encounter in their work:

a. Selection bias results from poor selection of the sample population to measure/ study. Also called design bias or sample error, it occurs when the people, place or time period measured is not representative of the larger population or condition being studied. It is a very important concept to understand because there is a tendency to study the most successful and/or convenient sites or populations to reach.

b. Measurement bias results from poor data measurement – either due to a fault in the data measurement instrument or the data collector. Sometimes the direct measurement may be done incorrectly, or the attitudes of the interviewer may influence how questions are asked and responses are recorded.

c. Processing error results from the poor management of data – miscoded data, incorrect data entry, incorrect computer programming and inadequate checking.

This source of error is particularly common with the entry of quantitative (statistical) data, for which specific practices and checks have been developed.

d. Analytical bias results from the poor analysis of collected data. Different approaches to data

analysis generate varying results e.g. the statistical methods employed, or how the data is separated and interpreted. A good practice to help reduce analytical bias is to carefully identify the rationale for the data analysis methods.

Data management systems can be designed to verify data accuracy and completeness, such as cross- checking figures with other data sources or computer double-entry and post-data entry verification when possible.

M&E Methodology

The proposed M&E system is oriented around a three-level framework within which to monitor implementation progress toward producing proposed outputs and assessing the impact of these outputs in inducing behavioral or systemic change and impact on targeted impact groups and wider development goals.

i. Output Monitoring: The first level refers to the regular and continuous monitoring of project activities, project processes, and the outputs produced as a result.

ii. Outcome Assessment: The second level relates to the monitoring and assessment of behavioural or systemic change that is being induced by the outputs produced by the project.

iii. Impact Assessment: Finally, the third level refers to the assessment of changes occurring in the quality of life on targeted impact groups (e.g, rural households and IDPs) as a result of the behavioural or systemic changes caused by the project. This impact includes both the impact on specific targeted impact groups as reflected in the project’s development objective, as well as the contributions that the project is making towards the achievement of its overall goal.

Developing an M&E Framework

A key feature of this part is the identification of a set of objectives, structured in a manner that

provides a firm foundation for the design, establishment, and operation of the M&E system. A number of M&E tools can be used to develop the M&E framework.

To setup the M&E system for  NYMA, six steps shall be followed:

1) The purpose and scope of the M&E system

Identifying the purpose and scope clarifies the need for M&E and how comprehensive should it be. It serves as a reference point for the M&E system, guiding key decisions such as informational needs, methodological approaches, capacity building and allocation of resources. The following outlines some key considerations when determining an M&E system’s purpose and scope:

i)	Review the project’s operational design (logframe).

The logframe is the foundation on which the M&E system is built. The logframe is a summary

of the project’s operational design, based on the situation and problem analysis conducted during the project’s design stage. It summarizes the logical sequence of objectives to achieve the project’s intended results (activities, outputs, outcomes and goal), the indicators and means of verification to measure these objectives, and any key assumptions.

A well-developed logframe reflects the informational needs of the project. For example, the objectives and informational needs of a project during an emergency operation will have very different logframe and related M&E requirements than a longer-term development project.

An important consideration in the logframe is the use of industry-recognized, standard indicators. Industry-recognized, standard indicators vary from sector or project area. The key types of industry-recognized indicators are set below:

- Industry indicators developed for use across the humanitarian industry.

- Sector-specific or thematic indicators developed for use in specific thematic sectors.

- Cluster indicators are particularly useful where outcomes and impact achieved cannot be attributed to the work of one organization, but rather to the collective efforts of multiple organizations in a cluster or across clusters.

- Organization-specific indicators which have been developed for use in specific operations or for organizational reporting against its strategy.

ii)	Identify key stakeholder informational needs and exceptions.

Planning an M&E system based on stakeholder needs and expectations helps to ensure understanding, ownership and use of M&E information. It is essential to have a clear understanding of the priorities and information needs of people interested in or affected by the project. This includes stakeholder motivations, experience and commitment, as well as the political and other constraints under which various beneficiaries operate. It is especially important that local knowledge is sought when planning M&E functions to ensure that they are relevant to and feasible in the local context, and that M&E information is credible, accepted

and more likely to be supported.

iii)	Identify any M&E requirements

Important informational needs worth specific attention are those that arise from any Donor guidelines and requirements, governmental laws and regulations, and internationally- agreed- upon standards. These requirements can include very detailed procedures, formats and resources, and are often non-negotiable. Therefore, it is best to identify and plan for them early in the M&E planning process.

Internationally-agreed-upon standards and criteria are particularly relevant to the  NYMA’s work. Interventions are often implemented through various partnerships within the industry, with bilateral financiers and between international, national and civil society organizations. It is important that work is conduct according to agreed-upon standards and criteria – which need to be monitored and evaluated.

2) Identifying performance questions, information needs and indicators

A performance question helps focus your information-seeking and information analysis processes on what is necessary in order to know if the project is performing as planned or, if not, why not. Once you have your performance questions, you can more easily decide what information you need to track rather than what is nice to track.

Working with performance questions to guide indicator analysis will give you more integrated and meaningful picture of overall project achievements. Answering these questions requires descriptive analysis and quantitative information. Starting by identifying performance question make it easier to recognize which specific indicators are really necessary. Sometimes a performance question can be answered directly with a simple quantitative indicator. However, very often the question can only be answered with a range of qualitative and quantitative information.

With performance questions, you can start identifying what information you need. This can include indicators and, possibly, additional background information that allows you to interpret the data from the indicators. Indicators will only ever show a partial view. They represent a simplification of approximation of a situation. An indicator simply helps communicate changes that are usually more complex. Using an indicator often means reducing data to the symbolic representation of a project objective, in a way that is relevant and significant for people who will use the information.

Therefore, multiple sources of qualitative and quantitative information are critical to explain what is happening and to look closely at relationships between different pieces of information, rather than single indicators. Almost any topic that needs to monitor can be assessed using either quantitative or qualitative indicators, according to the kind of information needed. When working with indicators to assess impact, the attempt is to create an overall picture built of various aspects. However, one indicator or even several will not be adequate to understand the changes. For impact assessments, a description analysis rather than single indicators often better capture the overall changes.

Examples for the basic performance questions per level of the objective hierarchy:

	Activities – What has been actually done?

	Outputs – What has been delivered as a result of project activities (e.g., number of people trained)?

	Outcomes (results) – What has been achieved as a result of the outputs (e.g., extent to which those trained are effectively using new skills)?

	Impacts – What has been achieved as a result of the outcomes? What contribution is being made to the goal? Are there any unanticipated positive or negative impacts?

	Lessons – What has been learned from the project that can contribute to improved project implementation or to building relevant fields of knowledge?

Other examples performance questions include:

	how have the purchasing power of target households as compared to non-target groups? What external factors have influenced any changes?

	to what extent are target households better able to meet their housing, education and health needs than non-target households?

	how have the diversity, production and productivity of agriculture in the target area changed as a result of project activities and as a result of external factors?

Define appropriate indicators

Once performance questions and information needed have been determined, indicators need to be defined or reviewed. Ideally this level of planning should be conducted within the project planning process, and influence the logframe resulting from it. However, this is not always possible, and many indicators may have been set in draft form in the initial logframe plan.

Ideally, different types of indicators for each result and related performance question(s) need to be determined. These can be of the following:

Once these have been defined, the nature of the indicator needs consideration. There are three broad categories of indicators that are used most often:

  Quantitative: This is often stated in the form of numbers. They are most often related to the total of activity implemented or outputs produced within a specified period of time;

  Qualitative: This reflects a change in quality, in the form of changes in attitude.. etc. It may be reflected in perceptions, or numbers (% change);

  Proxy: These “indirect” indicators are used when it is difficult to directly measure a result, or change. An indicator that is symbolic is to be determined, or approximate to the change under measurement. For example, if we find difficulty in directly measuring improvements in household income, we may determine an indicator that measures increased purchasing of a necessary household item, or increased savings. Proxy indicators rely on cause and effect.

An important consideration in defining indicators is that of attribution. This refers to the extent to

which the change you are measuring is directly attributable, or the result of,  NYMA’s project activities. In many instances change is the result of a range of different contributing factors, so it is important to be realistic and specific about what change is measured as the consequence of the project. The more specific the indicator is identified, the better.

3) Planning for information gathering and organizing

For each information need or indicator, you must establish how the information will be collected and organized. Not only will each indicator require choosing a different method, but for each indicator or information need you will usually present several options. There are many methods – qualitative and quantitative and individual versus group-based.

Particularly critical at the moment of method selection is knowing who will be involved in collecting, compiling and analyzing. The more the intended users of the methods can be involved in selecting or developing the methods, the more the chance that they will understand and apply them correctly.

If methods are selected by someone other than the users, training on the selected methods shall be essential.

Gathering data is one thing. But each bit of information also needs to be collated, perhaps summarized and certainly analyzed by the right people.

4) Planning for data processing

Collected information needs to be collated, perhaps summarized and analyzed by the right people. Seeing monitoring as a learning process implies that analysis and agreeing on decisions are undertaken within all levels of  NYMA personnel in the project hierarchy and with partners. As a general rule, data collection and analysis should be undertaken with those people to whom the data, analysis and decisions pertain. Data entry and processing requires specific skills and tools. If the skills are not available within the project, arrangements need to be made to help team members to acquire data analysis skills. Data can be collected on paper forms or voice recorders, or may be entered directly into databases using handheld computers. Validity checks need to be incorporated into data entry processes, and procedures for data filtration have to be developed, to optimize data quality. Computers assigned for data analysis should be equipped with data analysis software (e.g., SPSS softwares). Making sense of the data generated by M&E processes and assessing the implications for the project strategy and operations are the two important building blocks of M&E that typically get little attention. Do not rely on the Log Frame matrix as it does not give any reference to this aspect of M&E.

5) Planning for quality communication and reporting

M&E related findings have many potential audiences. When reporting on progress with the Annual Work Plan & Budget (AWPB), you will direct yourself to funding agencies, steering committees, cooperating institutions and implementing partners. Primary beneficiaries have a right to know overall the extent to which the project is progressing and they deserve the opportunity to conclude on initial findings. Funding agencies, such as DONOR, EU and Islamic Bank of Dubai, and  NYMA managers need information on impact, while all implementing partners need to understand problems in order to come up with remedies. Two sets of M&E findings will need to be communicated.

First, it is good practice to discuss draft M&E findings with implementing partners and primary beneficiaries in order to get feedback on accuracy, reach joint conclusions and agree on next steps. Once the M&E findings are agreed upon, these can be communicated to funding agencies, cooperating institutions, government departments and other projects.

The second set of final findings will fulfill accountability needs; however, can also serve for advocacy purposes.

6) Planning for the necessary conditions and capacities

The  NYMA establishment planning documents have included the budget for M&E and the necessity of its existence. Yet, getting the M&E system working means planning for appropriate incentives, ensuring you have the right and enough human capacity at hand, and thinking about means and methods of storing and sharing information.

M&E in-charge personnel should obtain answers for the key questions listed below, when detailing

Developing an M&E Process Map

Logical Planning Framework

Logical planning framework (log frame for short) is a matrix that allows to further develop the work performed in the planning stage. While the results framework is a snapshot of a project’s higher-level objectives, the log frame provides information about its activities, the performance indicator(s) for each objective, a brief description of how data will be measured or collected, and any critical

assumptions that underpin the project’s theory of change. The matrix used in the log frame is shown in

the table below.

Constructing a log frame follows a general pattern, but it is also an interactive and dynamic process in which many drafts will develop before finalizing one.

A log frame, sometimes called an M&E framework or performance management plan, is a tool to assist with project planning, design and monitoring and evaluation.

The log frame is a matrix that outlines:

● What activities will be undertaken to achieve what results;

● How these results will be measured (what indicators and what tools);

● A ‘project logic’ describing the causal links between input, output, outcomes and impact.

A log frame should be used throughout the program implementation to develop annual or monthly targets against which performance should be measured. A log frame aims to enable learning and continuous improvement that links accountability for resources to the results, outcomes and impacts they produce.

Basic components of a log frame include:

Goal – the higher objective to which  NYMA project and others will contribute;    Purpose/Outcomes – the effect of  NYMA project on the targeted population;

Outputs – the project deliverables for which  NYMA can be held accountable;

Activities – principle project activities, organized by output.

The logical framework matrix is a way of presenting the substance of an intervention in a comprehensive form.

  The vertical logic (or intervention logic) identifies what the project intends to do, clarifies the causal relationships and specifies the important assumptions and risks beyond the project manager’s control.

  The horizontal logic relates to the measurement of the effects of, and resources used by the project through the specification of key indicators, and the sources where they will be verified.

Writing the M&E Narrative

In the narrative, you will describe the project monitoring system and planned evaluations. Readers of the M&E narrative should be able to judge the appropriateness of plans set, and have confidence in M&E personnel’s ability to undertake the proposed M&E activities. Financiers almost have their own specific requirements for the content of the M&E narrative, so Donor guidance should be followed where applicable.

Broadly speaking, the M&E narrative should describe M&E unit’s plans for the following:

• Project monitoring

• Baseline, mid-term and final evaluations

Project Monitoring

The narrative will be based on the completed results framework and logical planning framework. It describes the proposed system that will ensure performance indicator data are collected, analyzed, and reported. The M&E narrative is an opportunity to describe in more detail the methods that you are intending to use to collect and analyze data, and report ongoing project progress and achievement of the strategic objectives. The narrative should describe the participation of beneficiaries in the M&E system so that their contributions can inform internal decision-making and project reporting.

The narrative should include a description of how the data generated will be used by project staff to assess the need for modifications to planned project operations. It is important to briefly describe your plans for internal project meetings and other reflective events that will utilize information generated by the project monitoring system.

Depending on the scale and complexity of the project, it may be useful to include other M&E tools that further define the M&E system, including the two listed below:

• Indicator Performance Tracking Table – to provide details of the baseline values (where available) and performance targets that have been set for each year of the project for large-scale projects. For smaller projects, it may be simpler to integrate the target information with the performance indicator statement in the second column of the log frame.

• M&E Calendar – to provide a detailed schedule for the M&E activities and events you are planning, including the establishment of the M&E system itself.

Baseline, Mid-term and Final Evaluations

The project’s size and complexity will to a large extent determine how the baseline and final evaluations are best conducted. Usually, external M&E service providers conduct the final evaluation. The narrative will indicate when it is expected to undertake both the baseline and final evaluations and an outline of the evaluation method to be used.

It might be decided that the project duration merits a mid-term review. The narrative shall be used to describe its purpose, the kind of information expected to generate, and how that information will be used to guide subsequent project operations.

Implementing the M&E system

Information gathering and organizing

Information involves adding meaning to data (raw material) by synthesizing and analyzing it.

Knowledge emerges when the information is related back to a concrete situation in order to establish explanation and lessons for decisions.

For each information need or indicator, you must establish how the information will be collected and organized. Monitoring progress is relatively straightforward. Monitoring the impact requires a different method. Not only will each indicator require choosing a different method, but also each indicator or information need will usually present several options. Each method has specified advantages and disadvantages in terms of cost, reliability of data, skill needed, ability to quantify results and richness

of information generated.

Gathering data is one thing. But each bit of information also needs to be collated, perhaps summarized and certainly analyzed by the right people. This will need to be planned in detail at start up. Project field staff are often only involved as data collectors and primary beneficiaries only as data providers. Seeing monitoring as a learning process implies that analysis and agreeing on actions are undertaken with all levels in the project hierarchy and with partners. As a general rule, data collection and analysis should be undertaken with those to whom the data, analysis and decisions pertain and therefore, at the relevant level.

Data collection methods

There are many methods commonly used for M&E. They have been grouped as follows:

Sampling methods;

Core M&E methods (such as beneficiaries analysis and questionnaires);

Discussion methods for groups (such as brainstorming and role plays);

Methods for spatially-distributed information (such as maps and transects);

Methods for time-based patterns of change (such as diaries and photographs);

Methods for analyzing relationships and linkages (such as impact flow diagrams and problem trees);

Methods for ranking and prioritizing (such as matrices).

Before selecting your methods, first consider three important aspects:

Quantitative versus qualitative methods;

Individual versus group-based methods;

The extent to which a method can be participatory.

Collecting secondary data and information

-	Compilation of data from project staff/agency records or service providers’ records.

This is recommended for activity (therefore output) monitoring of projects. This can provide information concerning the whole beneficiaries’ universe, offer basic performance information. At the same time, it’s essential for accountability purposes (e.g. show what the project budget was spent for).

-	Compilation of data from beneficiaries’ records:

This is the best when groups of beneficiaries are formed (if project deals with individual households, this will be too complicated). This method is good for outcome and impact monitoring (e.g. if beneficiary groups are requested to keep records/information on agricultural/dairy production; volumes of sales; incomes, etc.). Through it, whole or part of beneficiaries’ universe can be monitored. This can inform on qualitative aspects as well and be a good tool for impact monitoring… but at a cost. In addition, it demands in terms of human resources and project MIS.

Applicable  methods  to  NYMA’s  M &E  data  coll ecti o n

Survey

Survey is an effective method to capture information on a small sample that represents the beneficiaries. To be achieved, this method should be used many times undergoing strict requirements for sampling skills and investigator management. During the project implementation, the project should carry out the following surveys:

(1) Baseline survey

The baseline survey will involve mainly the collection of quantitative data against the project’s outcome, objective and goal levels. This will include the collection of both secondary data where appropriate and primary data where secondary data sources cannot provide sufficient information. Secondary data sources include the General Statistics Office and sources from within the project’s stakeholders, including the Ministry of Planning and International Cooperation in Yemen and the Ministry of Agriculture and Irrigation. The quantitative survey will be population based – meaning that the data will be collected not only from targeted direct beneficiary households but also from non- beneficiaries in order to accurately gauge the impact of the project, including the ripple effects of the project. Information emerging from the baseline survey will be analyzed by beneficiaries at the

province and district level in each province in an analysis workshop to determine whether and how the baseline findings should influence project implementation or strategy.

(2) Annual Outcome Survey

Annual surveys will be conducted to obtain quantitative information on indicators at the outcome and objective levels. These annual surveys are basically a condensed replication of the baseline, mid-term and end-line surveys to provide information for decision makers in the event that a strategic change needs to be made before an evaluation occurs. They are also a critical capacity building tool for M&E project staff to obtain and use M&E information.

(3) End-line survey

Near the end of the final year of the project, a final evaluation will be conducted to assess the impact that has been achieved by the project as well as to identify lessons learned and good practices generated by the project. As with the mid-term evaluation, the final evaluation will include both a quantitative end-line survey to collect data against the project’s outcome, objective and goal level indicators, as well as collection of qualitative information to understand how and why impact has been achieved. The end-line quantitative survey will be a population-based, and the data will be collected, analyzed and made available before the qualitative information gathering phase of the evaluation

begins. As with the mid-term evaluation, the qualitative evaluation is recommended to be conducted by a team of external evaluators to determine the reasons behind the changes reflected in the quantitative data comparisons between baseline and end-line have occurred. This team will also look for other impacts that might have been achieved but not captured by the quantitative survey.

Key informant interview

A key informant interview is a dialogue between researchers and people who can provide detailed information (hereinafter called ‘interviewee’) in order to understand interviewees’ lives, experiences and perception on particular issues. This is the best method in case of sensitive information. It is also very effective in finding solutions, suggestions, or new ideas.

Focus group discussion

Focus group discussion (also known as intensive group discussion, focus group interview; hereinafter referred to as “focus group”) aims to obtain qualitative information on attitude, perception, opinion and idea from a group of people who have in-depth understanding about the subject matter.

This method is used to collect detailed qualitative information from groups of 8-12 people with common characteristics and allow a deep understanding about the behavior, attitudes, feelings, perceptions and perspectives of the beneficiary. Group discussions are often used to assess the needs,

collect opinion from many people to evaluate the problem underhand, or discuss controversial content, or collect new ideas.

Observation method

In addition to project reporting,  NYMA project staff from head office will be responsible for conducting periodic field visits to observe project activities. They will document their observations in concise field trip reports that will also describe their plans for addressing any problems or opportunities they have observed. These field trip reports will be attached to quarterly reports in the project reporting system so that they can be considered by decision-makers at various levels.

Supervision mission

Supervision missions will be carried out by Donor, in its capacity as the oversight agency, to review the progress towards the objectives and to help with the development of project plan. The supervision missions will use a qualitative approach but will also review the survey results and other qualitative and quantitative data collected and reported by the project. The supervision mission will check the quality of results presented in the survey report and other monitoring reports.

Options for verifying data

Every project needs its own way to incorporate verification into its data-collection process. Triangulation is an important method for checking data. This means collecting the same type of information but from different sources and using different methods. This can be simple as, for example, asking the same question with different focus groups or comparing the outputs of a map and a transect of the same area. Typically, a simple triangulated method involves the knowledge and experience of the reviewer, the input from the review participant, and documentary information. Verifying quantitative data is often more straightforward, as more agreed standards exist. These involve statistical checks and validation exercises, in order to confirm the consistency of results.

How to collate information

Collation of information requires an appropriate format. With some methods, this is very straightforward process, although the collation of qualitative data often requires special care and analytical skills.

Analyzing M&E findings requires looking closely at the information (ideas, facts, and impressions), clarifying and structuring it, understanding connections and identifying core elements, in order to arrive at conclusions that can lead to action.

Analyzing M&E findings has several functions:

  To refine understanding – by discussing initial information with project beneficiaries, more refined insights can emerge;

  To limit biases – ensuring a thorough discussion about information means that this is cross checked and people can point out when they feel an issue has been represented incorrectly;

  To build a clear picture of a situation/event/process and reach consensus – by discussing data, contradiction and gaps can be identified and can be understood or filled;

  In participatory M&E joint analysis can strengthen ownership of the conclusions and motivate

people to invest more in making changes happen.

The ones that will undertake analysis and those that will be involved, should be considered. Choosing a method for analysis depends on various factors, including whether it will be a participatory process,

the tool you use to collate and analyze the data (e.g. a computer), and the type of information that is being collected.

Storing M&E information

Documentary information is critical for M&E as it provides the basis for communication, transparency, consensus building, and continuity of consultative processes. Stored information serves as the source

of institutional memory turned to by newcomers and when verification or comparison with the past is needed.

-	What information needs to be stored? – Information storage is needed at two levels: to guide the project strategy and for tracking operations. In principle everything you decide to monitor and evaluate will need to be stored in some way.

-	Who needs to access the information and when? – How the data are stored depends on who is to have access to the information and how often. Information to guide the project strategy is critical for managers (project staff and implementing partners), steering committees, primary stakeholder representatives and funding agencies. Information on operations is critical for field workers, managers of project component and primary beneficiaries.

-	What type of information needs to be stored? – Hard copies or data that can be retrieved electronically. The more parties that need the information the better to store in scanned and soft copies.

Though not all information should be stored resulting in overwhelming the data storage management (archive) and the difficulty to keep updated, a regular assessment should be made to decide on which information needs to be maintained and which can be discarded.

Participation and M&E

People involved in a development intervention will make it either succeed or fail. Their participation in learning how to improve a project throughout its existence is fundamental. For  NYMA and partner staff, this means listening carefully and regularly to the views of different groups – including each other – about what is working and what is not, and hearing reasons for why problems exist and what needs to improve. Learning certainly requires more than only “listening”. Opportunities need to be created for staff from the project and implementing partners and primary beneficiaries to meet and analyze their experiences with the project.

Responsibilities

M&E is part of all  NYMA personnel’s job. Monitoring is a daily and spontaneous activity. Yet it is important that M&E functions should be well positioned within  NYMA’s organization chart to reflect its importance and independence. The overlaps between project management (each program activity) and M&E function should be mitigated if not reduced. M&E staff should be well equipped and qualified to carry out such supervisory, analytical, and monitoring process on  NYMA’s conducted programs. This includes having job descriptions drafted for each M&E team member, clarifying their roles in data inputs, interpretations, and reporting.

Communication of M&E Results

M&E findings have many potential audiences: funding agencies, steering committees cooperating institution, project and implementing partners, and primary beneficiaries. The main purpose of communicating findings is to ensure accountability and motivate beneficiaries to act, drawing their attention to project status and circumstances.

A key communication task is to ensure that findings raised are correct and valid, prior to finalizing the report. Workshops and meetings are critical events to seek feedback and plan action. When planning to present M&E information for feedback, ensure the message clarity for specified audience, agree on the frequency of communicating information, and ensure timeliness.

Use different media to communicate findings – it is not often that “one message speaks to all”. Written reporting is most well-known and ranges from formal progress reports, to special studies, to informal briefs in the form of memorandums highlighting a current issue. However, under certain

circumstances, M&E findings can be communicated more effectively verbally than by other means. Speaking directly with target audiences provides a quicker and more flexible way to convey messages. Also the use of visual displays, such as graphs or charts, showing trends or maps to convey summaries of what is happening helps delivering the information easily.

Implementing a Learning System

Critical reflections can occur formally and informally. Formally, it can be facilitated during project meetings, workshops with partners and primary beneficiaries or as part of external evaluations. Informally, it can occur in ongoing discussions between project beneficiaries. Reflecting critically means questioning what is normally taken for granted, particularly project assumptions. This requires reflecting on what did not work or is not working.

Project M&E involves an extensive series of potentially reflective events – from weekly team meetings and informal sessions to the more formal supervision mission and mid-term reviews/evaluations. These events, whether self-organized or externally initiated, occur alongside data gathering. During these events, project staff can use the data gathered to indicate areas of improvement.

Learning does not happen in one sitting. It evolves, starting with individuals raising important issues and questioning assumptions through group based analyses that bring out different perspectives and information inputs. So “learning” as a series of events, should be considered from the beginning. Knowing how to structure the sequence is important. The optimal sequence of learning events follows reporting lines and hierarchies of decision-making.

An important moment in the learning sequences is when lessons are identified. Project and partner staff are continually learning, sometimes unconsciously and changing their everyday actions accordingly. Sometimes it is useful to systematize this learning in the form of “lessons learned”. A lesson learned can have an internal audience – the project and partner themselves – as well as an external audience consisting of other projects, and other funding agencies.

Making M&E events more reflective

Critical refection occurs in everyday planning, implementation and M&E activities. Each person involved in the project filters or changes information, prioritizing and rejecting data continuously and often unconsciously. This happens in each informal chat, as well as during formal external missions.

Making a project reflective, means planning more consciously about when and how to deal critically with information.

Using steering groups for reflection

It is recommended that  NYMA uses a steering committee of some sort to provide strategic guidance. Of primary importance in the establishment of the steering committee is to define the clear extent – and limits – of responsibility. Once this is clear and agreed, and this can occur as part of project formulation, then the committee’s composition and frequency of meetings can be decided.

To use steering committees as learning opportunities, the meetings to assess dilemmas and problems and finding solutions can be used – rather than to report progress, as progress can be shared in documents beforehand. The steering group members can be invited to visit the field(s) at several times during the project life and interact with field staff and targeted beneficiaries.

Annual project review

External project reviews are a considered a standard method of assessing progress. However, internal annual reviews are also important for reflection. The overall purpose of the annual project review is to reach conclusion about achievements and failures in order to improve ongoing program quality, and to share these conclusions. An annual project review can also help to:

* Ensure the overall project goals, results and implementation strategy remain appropriate;

* Assess progress towards planning impacts;

* Review implementation to date and analyze reasons for any deviations;

* Review the operational and management effectiveness and efficiency of implementation;

* Identify lessons and actions to improve next year’s implementation and performance.

Responding to unplanned needs and request for information

It is expected that  NYMA’s M&E unit will often receive sudden demands from the CEO, project managers, ministries, steering committee, and funding agencies to provide a report on a specific issue, or some other type of information. When developing the budget include a budget line for unplanned costs, approximately 10% contingency allocation.

Reporting and utilization

Reporting is the most visible part of the M&E system, where collected and analyzed data is presented in the form of information for key beneficiaries to use. Reporting is a critical part of M&E because no matter how well data may be collected and analyzed, without being well presented, it cannot be properly used, which can be a considerable waste of valuable time, resources and personnel effort.

I. Anticipate and plan for reporting

Reporting can be costly in terms of time and resources and should not become an end in itself, but serve as a well-planned purpose. Therefore, it is critical to anticipate and carefully plan for reporting.

Key reporting characteristics that ensure its usability:

-	Relevant and useful. Reporting should serve a specific purpose/use. Avoid excessive, unnecessary reporting – information overload is costly and can burden information flow and the potential of using other relevant information.

-	Timely. Reporting should be timely for its intended use. Information is of little value if it is too late or infrequent for its intended purpose.

-	Complete. Reporting should provide a sufficient amount of information for its intended use. It is especially important that reporting content includes any specific reporting requirements.

-	Reliable. Reporting should provide an accurate representation of the facts.

-	Simple and user-friendly. Reporting should be appropriate for its intended audience. The language and reporting format used should be clear, concise and easy to understand.

-	Consistent. Reporting should adopt units and formats that allow comparison over time, enabling progress to be tracked against indicators, targets and other agreed-upon milestones.

-	Cost-effective. Reporting should warrant the time and resources devoted to it, balanced against its relevance and use.

A valuable tool when planning for reporting is a reporting schedule, matching each reporting requirement with its frequency, audience/purpose, format/outlet and person(s) responsible.

A. Identify the specific reporting needs/audience

Reports should be prepared for a specific purpose/audience. This informs the appropriate content, format and timing for the report. For example, do users need information for ongoing project/program implementation, strategic planning, compliance with Donor requirements, evaluation of impact and/or organizational learning for future project/programs?

| Internal reporting | External reporting |
| --- | --- |
| • Primary audience is the project/ program team and the organization ( NYMA) in which it operates. | • Primary audience is beneficiaries outside of the immediate team/ organization (e.g. Donors, beneficiaries, partner organizations, International bodies, and governments). |
| • Primary purpose is to inform ongoing project management and decision-making (Monitoring reporting). | • Primary purpose is typically for accountability, credibility, to solicit funds, celebrates accomplishments and highlights any challenges and how they are being addressed. |
| • Frequency is on a regular basis according to project monitoring needs. | • Frequency is less often in the form of periodic assessments (evaluations). |
| • Content is comprehensive in content, providing information that can be extracted for various external reporting needs. | • Content is concise, typically abstracted from internal reports and focused on communication points (requirements) specific to the targeted audience. |
| • Format is typically determined by the requirements or preferences of intended audience. | • Format is often determined by external project team according to what will best serve the project/ programme needs and its organizational culture. |

As already noted, it is best to identify reporting and other informational needs early in the M&E planning process, especially any reporting requirements.

A particularly important consideration in planning for reporting is the distinction between internal and external reporting (see table below).

Internal reporting is conducted to enable actual project implementation; it plays a more crucial role in lesson learning to facilitate decision-making – and, ultimately, what can be extracted and reported externally. External reporting is conducted to inform beneficiaries outside the project/program team and implementing organization; this is important for accountability.

Day-to-day operations depend upon a regular and reliable flow of information. Therefore, special attention should be given to the informational needs of the project/program managers. Timely information will be needed to analyze progress and critical issues, make planning decisions and prepare progress reports for multiple audiences, (e.g. superiors and financiers). In return, project-level reports provide essential information for program managers and CEO to compare planned actions with actual performance and budget.

B. Determine the reporting frequency

It is critical to identify realistic reporting deadlines. They should be feasible in relation to the time, resources and capacity necessary to produce and distribute reports including data collection, analysis and feedback.

Some key points to keep in mind in planning the reporting frequency:

1. Reporting frequency should be based upon the informational needs of the intended audience,

timed so that it can inform key project/program planning, decision-making and accountability events.

2. Reporting frequency will also be influenced by the complexity and cost of data collection. For instance, it is much easier and affordable to report on a process indicator for the number of workshop participants than an outcome indicator that measures behavioural change in a random sample, farmers’ income survey (which entails more time and resources).

3. Data may be collected regularly, but reporting timings might vary from a party to another. Some financiers might require quarterly reports, while CEO requires a monthly or weekly report. Monitoring agency, DONOR, will need a baseline (at the start of the project) and end-line assessment (at the final stage of the project).

C. Determine specific reporting formats

Once the reporting audience (who), purpose (why) and timing (when) have been identified, it is then important to determine the key reporting formats that are most appropriate for the intended user(s). This can vary from written documents to video presentations. Sometimes the reporting format must adhere to strict requirements, while at other times there can be more flexibility.

It is important that report formats and content are appropriate for their intended users. How information is presented during the reporting stage can play a key role in how well it is understood and put to use. For example, reports with graphs and charts may work well with project/program management, participatory discussion meetings with field staff, community (visual) mapping for beneficiaries and a formal report or website for financiers. Reporting should be translated in the appropriate language and in a culturally appropriate format (e.g. summary form, verbal or written).

Some practical tips to help make written reports more effective:

Box 22: Report writing tips

* Be timely – planning the report writing beforehand and allowing sufficient time.

* Involve others in the writing process, but ensure one focal person is ultimately responsible.

* Translate reports to the appropriate language.

* Use an executive summary or project overview to summarize the overall project status and highlight any key issues/actions to be addressed.

* Devote a section in the report to identify specific actions to be taken in response to the report findings and recommendations and the respective people responsible and time frame.

* Be clear, concise, avoiding long sentences – avoid jargon, excessive statistics and technical terms.

* Use formatting, such as bold or underline, to highlight key points.

* Use graphics, photos, quotations and examples to highlight or explain information.

* Be accurate, balanced and impartial.

* Use logical sections to structure and organize the report.

* Avoid unnecessary information and words.

* Adhere to any Donor formats, writing usage/style guidelines.

* Check spelling and grammar.

The project/program management report

Particular attention should be given to the project management report because it typically forms the basis for internal information that will, in turn, provide information for external reporting. Other reporting formats may occur more frequently, e.g. for specific activities, or less frequently, such as evaluation reports, but the project management report is usually the primary reporting mechanism for compiling information from various reports for project management and providing information for other reports serving accountability.

Project management reports should be undertaken at a frequency regular enough to monitor the project progress and identify any challenges or delays with sufficient time to adequately respond. It is recommended that  NYMA undertakes management reporting on a monthly and quarterly basis.

Monthly reporting allows for a more regular overview of activities which can be useful, particularly in a fast-changing context, such as during an emergency operation. However, more frequent data collection and analysis can be challenging if monitoring resources are limited. Quarterly reports allow for more time between reports, with less focus on activities and more on change in the form of outputs and even outcomes.

Project management report is recommended to include the following components:

1. Project information. Summary of key project information, (e.g. name, dates, manager, codes, etc).

2. Executive summary. Overall summary of the report, capturing the project status and highlighting key accomplishments, challenges, and planned actions. Also includes the indicators for people reached and volunteers.

3. Financial status. Concise overview of the project’s financial status based on the project’s monthly

finance reports for the reporting quarter.

4. Situation/context analysis (positive and negative factors). Identify and discuss any factors that affect the project’s operating context and implementation (e.g. change in security situation or a government policy, etc), as well as related actions to be taken.

5. Analysis of implementation. Critical section of analysis based on the objectives as stated in the project’s log frame.

6. Stakeholder (beneficiaries) participation and complaints. Summary of key beneficiaries’ participation and any complaints that have been filed.

7. Partnership agreements and other key actors. Lists and makes reference to project partners and agreements and any related comments.

8. Cross-cutting issues. Summary of activities undertaken or results achieved that relate to any cross- cutting issues (gender equality, environmental sustainability, etc).

9. Project staffing – human resources. Lists any new personnel or other changes in project staffing. Also should include whether any management support is needed to resolve any issue.

10. Exit/sustainability strategy summary. Update on the progress of the sustainability strategy to ensure the project objectives will be able to continue after handover to local beneficiaries.

11. Project management execution status. Concise update of the project’s key planning, monitoring,

evaluation and reporting activities.

12. Key lessons. Highlights key lessons and how they can be applied to this or other similar projects in future.

13. Report annex. Any supplementary information.

II. Information utilization

The overall purpose of the M&E system of  NYMA is to provide useful information.

There are many factors that determine the use of information. First are the actual selection, collection and transformation of data into usable information, which has been the topic of this manual so far.

Four primary ways in which M&E information is used:

Project/program management – inform decisions to guide and improve ongoing project/program implementation.

Learning and knowledge-sharing – advance organizational learning and knowledge-sharing for future programming, both within and external to the project/program’s implementing organization.

Accountability and compliance – demonstrating how and what work has been completed, and whether it was according to any specific Donor or legal requirements, as well as to the DONOR and others’ international standards.

Celebration and advocacy – highlight and promote accomplishments and achievements, building morale and contributing to resource mobilization.

A. Information dissemination

Information dissemination refers to how information (reports) is distributed to users. This can be seen as part of reporting, but dissemination here is highlighted separately to mean the distribution of the information (reports) rather than the actual preparation of the information into a report.

There is a variety of mediums to share information, and as with the reporting formats themselves, how reporting information is disseminated will largely depend on the user and purpose of information.

1. Printed materials - hardcopies distributed through mail or in person.

2. Internet communication - e-mail (and attachments), websites, blogs, etc

3. Live presentations - such as project/program team meetings and public meetings.

4. Telephone communication- includes voice calls, video calls, text-messaging, as well as other functions enabled on a mobile phone.

5. Television and filmed presentations.

6. Data show presentations.

Selection of the reporting medium should be guided by what is most efficient in time and resources, and most importantly suitable for the audience – a process that should ideally be completed with a reporting schedule.

	An internet-based reporting system may be best for communication between a project/program management team in the field and headquarters in Sana'a. Works also for reporting to the agency in-charge of oversight (Donor) and other financiers.

	Community meetings may be appropriate to report on data to beneficiaries who lack access to computers or are illiterate.

	Mobile phone texting may be most timely and efficient for volunteers to report on safety conditions from the field.

It is also important to remember that information dissemination should be multidirectional. This means that in addition to distributing information upwards to management, senior management and financiers, information flows should also be directed to field staff, partners and the beneficiaries themselves.

Another important consideration when distributing information is the security of internal or confidential information. Precautions should be taken to protect access to confidential information.

B. Decision-making and planning

Decision-making and planning  form the heart of data utilization. No matter how well the information is prepared or disseminated, it will ultimately be up to the user to decide when and how to put it to use. This is where M&E planning merges with project/program management, and the manner in which decisions are made and information is used will vary according to project/program, context and organizational culture. However, while information use is largely in the area of project/program and organizational management, there are two key considerations that can aid the use of information in decision-making and planning:

1. Beneficiary dialogue. Beneficiary discussion and feedback on information is critical for building understanding and ownership, and informing the appropriate response. This process can begin during the analysis, review and revision of reporting information, and can correspond with information dissemination outlets, such as meetings, seminars and workshops, web-based forums, teleconferences and/or organizational reporting and follow-up procedures.

For instance, the findings of an evaluation report are more likely to be understood and used if they are not limited to a printed report, but presented to key beneficiaries in a face-to-face forum that allows them to reflect and give feedback. Ideally, this can be done before the final draft of the report to confirm key lessons and inform realistic recommendations.